Software cost estimation
Software cost estimation

---
Topics covered
Agenda
- Estimation techniques for
  - Costs
  - Time
- Software productivity
- Project duration and staffing
- Estimation techniques
  - Functional/Object points
  - COCOMO
  - Delphi
  - Story points, Poker

---
Fundamental estimation questions
Fundamental estimation questions
- How much effort is required to complete an activity?
- How much calendar time is needed to complete an activity?
- What is the total cost of an activity?
- Project estimation and scheduling are interleaved management activities.

---
Software cost components
Software cost components
- Hardware and software costs.
- Travel and training costs.
- Effort costs (the dominant factor in most
  projects)
  - The salaries of engineers involved in the project;
  - Social and insurance costs.
- Effort costs must take overheads into account
  - Costs of building, heating, lighting.
  - Costs of networking and communications.
  - Costs of shared facilities (e.g library, staff restaurant, etc.).

---
Costing and pricing
Costing and pricing
- Estimates are made to discover the cost, to the developer, of producing a software system.
- There is not a simple relationship between the development cost and the price charged to the customer.
- Broader organizational, economic, political and business considerations influence the price charged.

---
Software pricing factors
Software pricing factors
- Market opportunity
  - Development organization may quote a low price because it wishes to move into a new segment of the software market. Accepting a low profit on one project may give the opportunity of more profit later. The experience gained may allow new products to be developed.
- Cost estimate
  - If an organization is unsure of its cost estimate, it may increase uncertainty its price by some contingency over and above its normal profit.
- Contractual terms
  - A customer may be willing to allow the developer to retain ownership of the source code and reuse it in other projects. The price charged may then be less than if the software source code is handed over to the customer.
- Requirements volatility
  - If the requirements are likely to change, an organization may lower its price to win a contract. After the contract is awarded, high prices can be charged for changes to the requirements.
- Financial health
  - Developers in financial difficulty may lower their price to gain a contract. It is better to make a smaller than normal profit or break even than to go out of business.

---
Pricing to win
Pricing to win
- The project costs whatever the customer can spend on it.
- Advantages:
  - You get the contract.
  - A detailed specification may be negotiated or an evolutionary approach used for system development.
- Disadvantages:
  - Probability of failure is high and probability that the customer gets the system he or she wants is low. Price do not accurately reflect the work required.
  - May be unethical and/or illegal (e.g. dumping). However, when detailed information is lacking it may be the only appropriate strategy.
  - The project cost is agreed on the basis of an outline proposal and the development is constrained by that cost.

---
Top-down estimation
Top-down estimation
- Start at the system level and assess the overall system functionality and how this is delivered through sub-systems.
- Usable without knowledge of the system architecture and the components that might be part of the system.
- Takes into account costs such as integration, configuration management and documentation.
- Can underestimate the cost of solving difficult low-level technical problems.

---
Bottom-up estimation
Bottom-up estimation
- Start at the component level and estimate the effort required for each component. Add these efforts to reach a final estimate.
- Usable when the architecture of the system is known and components identified.
- This can be an accurate method if the system has been designed in detail.
- It may underestimate the costs of system level activities such as integration and documentation.

---
Estimation techniques_clipboard0
Estimation techniques
- Expert judgment
  - Several experts on the proposed software development techniques and judgement the application domain are consulted. They each estimate the project cost. These estimates are compared and discussed. The estimation process iterates until an agreed estimate is reached.
- Estimation by analogy
  - This technique is applicable when other projects in the same application analogy domain have been completed. The cost of a new project is estimated by analogy with these completed projects.
- Parkinson’s Law
  - Parkinson’s law states that work expands to fill the time available. The Law cost is determined by available resources rather than by objective assessment. If the software has to be delivered in 12 months and 5 people are available, the effort required is estimated to be 60 person-months.
- Pricing to win
  - Choosing the most affordable alternative that fulfills the customer needs and that also will be successful against competition.
- Algorithmic cost modeling
  - A model based on historical cost information that relates some software cost modeling metric (usually its size) to the project cost is used. An estimate is made of that metric and the model predicts the effort required.

---
Estimation accuracy
Estimation accuracy
- The size of a software system can only be known accurately when it is finished.
- Several factors influence the final size
  - Use of COTS and/or open source components;
  - Programming language;
  - Distribution of the system.
- As the development process progresses then the size estimate becomes more accurate.

---
Estimate uncertainty
Estimate uncertainty

---
Software productivity
Software productivity
- A measure of the rate at which individual engineers involved in software development produce software and associated documentation.
- Not quality-oriented although quality assurance is a factor in productivity assessment.
- Essentially, we want to measure useful
  functionality produced per time unit.

---
Productivity measures
Productivity measures
- Size related measures based on some output from the software process. This may be lines of delivered source code, object code instructions, etc.
- Function-related measures based on an estimate of the functionality of the delivered software.
- Function-points are the best known of this type of measure.

---
Measurement problems
Measurement problems
- Estimating the size of the measure (e.g. how many function points).
- Estimating the total number of programmer months that have elapsed.
- Estimating contractor productivity (e.g.
  documentation team) and incorporating this estimate in overall estimate.

---
Lines of code
Lines of code
- What is line of code?
  - The measure was first proposed when programs were typed on cards with one line per card;
  - How does this correspond to statements as in Java which can span several lines or where there can be several statements on one line.
- What programs should be counted as part of the system?
- This model assumes that there is a linear relationship between system size and volume of documentation.

---
Productivity comparisons
Productivity caveats
- The lower level the language, the “more productive” is programmer
  - The same functionality takes more code to implement in a lower-level language than in a high-level language.
- The more verbose is programmer, the “more productive” he is
  - Measures of productivity based on lines of code suggest that programmers, who write verbose code are more productive than programmers who write compact code.

---
Productivity estimates
Productivity estimates
- Real-time embedded systems:
  40-160 LOC/P-month.
- Systems programs:
  150-400 LOC/P-month.
- Commercial applications:
  200-900 LOC/P-month.
- In object points, productivity has been measured between 4 and 50 object points/month depending on tool support and developer capability.

---
Function points
Function points
- Function points (FP) are based on a combination of program characteristics:
  - external inputs and outputs;
  - user interactions;
  - external interfaces;
  - files used by the system.
- A weight is associated with each of these and the function point count is computed by multiplying each raw count by the weight and summing all values.
  FP = ∑(number of elements of given type)×weight

---
Function points
Functional Points to LOC
- The function point count is modified by complexity of the project
- FPs can be used to estimate LOC depending on the average number of LOC per FP for a given language
  - LOC = AVC * FP
  - AVC is a language-dependent factor varying from 200-300 for assemble language to 2-40 for a 4GL;
- FPs are very subjective. They depend on the estimator
  - Automatic function-point counting is impossible.

---
Object points
Object points
- Object points (alternatively named application points) are an alternative function-related measure to function points when “object-oriented” languages are used for development.
- Object points are NOT the same as object classes.
- The number of object points in a program is a weighted estimate of
  - The number of separate screens that are displayed;
  - The number of reports that are produced by the system;
  - The number of program modules that must be developed to supplement the database code;

---
Object point estimation
Object point estimation
- Object points are easier to estimate from a specification than function points as they are simply concerned with screens, reports and programming language modules.
- They can therefore be estimated at a fairly early point in the development process.
- At this stage, it is very difficult to estimate the number of lines of code in a system.

---
The COCOMO model
The COCOMO model
- Constructive Cost Model
- An empirical model based on project experience.
- Well-documented, ‘independent’ model which is not tied to a specific software vendor.
- Long history from initial version published in 1981 (COCOMO-81) through various instantiations to COCOMO 2.
- COCOMO 2 takes into account different approaches to software development, reuse, etc.

---
Basic COCOMO
- Cost is estimated as a mathematical function of
  product, project and process attributes whose
  values are estimated by project managers:
  - Effort = A×SizeB×M
  - A =2.94 initially, but is an organization-dependent constant
  - Size = approx KLOC — code prom functional points or other estimation
  - B = 1..1.5 reflects the disproportionate effort for large projects and
  - M is a multiplier reflecting product, process and people attributes.
- Most models are similar but they use different values for A, B and M.

---
COCOMO 2 models
COCOMO 2 models
- COCOMO 2 incorporates a range of sub-models that produce increasingly detailed software estimates.
- The sub-models in COCOMO 2 are:
  - Application composition model. Used when software is composed from existing parts.
  - Early design model. Used when requirements are available but design has not yet started.
  - Reuse model. Used to compute the effort of integrating reusable components.
  - Post-architecture model. Used once the system architecture has been designed and more information about the system is available.

---
Use of COCOMO 2 models
Use of COCOMO 2 models

---
Project types
- Organic
  A development project can be treated of the organic type, if the project deals with developing a well-understood application program, the size of the development team is reasonably small, and the team members are experienced in developing similar methods of projects. Examples:
  - simple business systems,
  - simple inventory management systems,
  - Simple data processing systems.
- Semidetached
  A development project can be treated with semidetached type if the development consists of a mixture of experienced and inexperienced staff. Team members may have finite experience in related systems but may be unfamiliar with some aspects of the order being developed. Examples:
  - new operating system (OS),
  - Database Management System (DBMS)
  - complex inventory management system.
- Embedded
  A development project is treated to be of an embedded type, if the software being developed is strongly coupled to complex hardware, or if the stringent regulations on the operational method exist.
  Examples:
  - Process controllers (Internet of Things)
  - Electrical devices, manufacturing devices, etc.
  - Traffic control systems
  - Embedded systems in cars, equipment etc.

---
Intermediate COCOMO
The Intermediate Cocomo formula now takes the form:
E=∑ai(KLoC)(bi)×EAF
where E is the effort applied in person-months, KLoC is the estimated number of thousands of delivered lines of code for the project, and EAF is the factor calculated before.
The Development time D calculation uses E in the same way as in the Basic COCOMO.
The coefficient ai and the exponent bi are given in the next table.
Software project	ai	bi
Organic	3.2	1.05
Semi-detached	3.0	1.12
Embedded	2.8	1.20

---
Intermediate COCOMO
- Intermediate COCOMO computes software development effort as function of program size and a set of "cost drivers" that include subjective assessment of product, hardware, personnel and project attributes. This extension considers a set of four "cost drivers", each with a number of subsidiary attributes:
  - Product attributes
  - Required software reliability
  - Size of application database
  - Complexity of the product
  - Hardware attributes
  - Run-time performance constraints
  - Memory constraints
  - Volatility of the virtual machine environment
  - Required turnabout time
  - Personnel attributes
  - Analyst capability
  - Software engineering capability
  - Applications experience
  - Virtual machine experience
  - Programming language experience
  - Project attributes
  - Use of software tools
  - Application of software engineering methods
  - Required development schedule
- Each of the 15 attributes receives a rating on a six-point scale that ranges from "very low" to "extra high" (in importance or value). An effort multiplier from the table below applies to the rating.
- The product of all effort multipliers results in an effort adjustment factor (EAF). Typical values for EAF range from 0.9 to 1.4.

---
Multipliers
Multipliers
- Product attributes
  - Concerned with required characteristics of the software product being developed.
- Computer attributes
  - Constraints imposed on the software by the hardware platform.
- Personnel attributes
  - Multipliers that take the experience and capabilities of the people working on the project into account.
- Project attributes
  - Concerned with the particular characteristics of the software development project.

---
Early design model
- Estimates can be made after the requirements have been agreed.
- Based on a standard formula for algorithmic models:
  PM = A  SizeB  M
  where:
  A = 2.94 in initial calibration, Size in KLOC
  M = PERSRCPXRUSEPDIFPREXFCILSCED
  B varies from 1.1 to 1.24
  depending on novelty of the project, development flexibility, risk management approaches and the process maturity.

---
The reuse model
The reuse model
- Takes into account black-box code that is reused without change and code that has to be adapted to integrate it with new code.
- There are two versions:
  - Black-box reuse where code is not modified. An effort estimate (PM) is computed.
  - White-box reuse where code is modified. A size estimate equivalent to the number of lines of new source code is computed. This then adjusts the size estimate for new code.

---
Post-architecture level
- Uses the same formula as the early design model but with 17 rather than 7 associated multipliers.
- The code size is estimated as:
  - Number of lines of new code to be developed;
  - Estimate of equivalent number of lines of new code computed using the reuse model;
  - An estimate of the number of lines of code that have to be modified according to requirements changes.

---
The exponent term
The exponent
B = 1.01 + 0.01×Wi
Wi depends on 5 scale factors:
Scale factor	Explanation
RESL — Architecture/risk resolution	Reflects the extent of risk analysis carried out. Very low means little analysis; extra-high means a complete and thorough risk analysis.
FLEX — Development flexibility	Reflects the degree of flexibility in the development process. Very low means a prescribed process is used; extra-high means that the client sets only general goals.
PREC — Precedentedness	Reflects the previous experience of the organization with this type of project. Very low means no previous experience; extra-high means that the organization is completely familiar with this application domain.
PMAT — Process maturity	Reflects the process maturity of the organization. The computation of this value depends on the CMM Maturity Questionnaire, but an estimate can be achieved by subtracting the CMM process maturity level from 5.
TEAM — Team cohesion	Reflects how well the development team knows each other and work together. Very low means very difficult interactions; extra-high means an integrated and effective team with no communication problems.

---
Function Point Analysis_clipboard0
Function Point Analysis
What is Function Point Analysis (FPA)?
- It is designed to estimate and measure the time, and thereby the cost, of developing new software applications and maintaining existing software applications.
- It is also useful in comparing and highlighting opportunities for productivity improvements in software development.
- It was developed by A.J. Albrecht of the IBM Corporation in the early 1980s.
- The main other approach used for measuring the size, and therefore the time required, of software project is lines of code (LOC) – which has a number of inherent problems.

---
Function Point Analysis_clipboard1
Function Point Analysis
How is Function Point Analysis done?
Working from the project design specifications, the following system functions are measured (counted):
- Inputs
- Outputs
- Files
- Inquires
- Interfaces

---
Function Point Analysis_clipboard3
Function Point Analysis
These function-point counts are then weighed (multiplied) by their degree of complexity:
	Simple	Average	Complex
Inputs	2	4	6
Outputs	3	5	7
Files	5	10	15
Inquires	2	4	6
Interfaces	4	7	10

---
Function Point Analysis_clipboard8
Function Point Analysis
Because function point analysis is independent of language used, development platform, etc. it can be used to identify the productivity benefits of...
  - One programming language over another
  - One development platform over another
  - One development methodology over another
  - One programming department over another
  - Before-and-after gains in investing in programmer training
  - And so forth...

---
Function Point Analysis
Function Point Analysis
But there are problems and criticisms:
  - Function point counts are affected by project size
  - Difficult to apply to massively distributed systems or to systems with very complex internal processing
  - Difficult to define logical files from physical files
  - The validity of the weights and the consistency of their application – has been challenged
  - Different companies will calculate function points slightly different, making intercompany comparisons questionable

---
The effect of cost drivers on effort estimates _clipboard2
Effect of multipliers on effort
Exponent value	1.17
System size (including factors for reuse and requirements volatility)	128,000 Delivered Source Instructions (DSI)
Initial COCOMO estimate without cost drivers	730 person-months
Reliability	Very high, multiplier = 1.39
Complexity	Very high, multiplier = 1.3
Memory constraint	High, multiplier = 1.21
Tool use	Low, multiplier = 1.12
Schedule	Accelerated, multiplier = 1.29
Adjusted COCOMO estimate	2,306 person-months
Reliability	Very low, multiplier = 0.75
Complexity	Very low, multiplier = 0.75
Memory constraint	None, multiplier = 1
Tool use	Very high, multiplier = 0.72
Schedule	Normal, multiplier = 1
Adjusted COCOMO estimate	295 person-months

---
Project duration and staffing
Project duration
- As well as effort estimation, managers must estimate the calendar time required to complete a project and when staff will be required.
- Most effective calendar time:
  TDEV = 3  (PM)(0.33+0.2*(B-1.01))
  PM is the effort computation and B is the exponent computed as discussed above.
- The time required is independent of the number of people working on the project.

---
Time vs Size

---
Staffing requirements
Staffing requirements
- Number of persons needed is calculated from optimal time:
  P = TDEV / PM
- Number of persons can’t be computed by diving the development time by the required schedule
- The more people who work on the project, the more total effort is usually required.
- A very rapid build-up of people often correlates with schedule slippage.

---
Effort vs Size

---
COCOMO precision
- Relies on Law of large numbers
  - If multipliers are many, some of them are overestimated, some are underestimated making total calculation more probable
  - Not precise under
    few person-months

---
Some online COCOMO calculators
- http://softwarecost.org/tools/COCOMO/
- http://groups.umd.umich.edu/cis/course.des/cis525/js/f00/gamel/cocomo.html

---
Planning poker as a variation of Delphi method
Delphi method
- The Delphi Method seeks to achieve a consensus among group members through a series of questionnaires.
- The series of questionnaires sent either by mail or via computerized systems, to a pre-selected group of experts.
- Nobody ‘looses face’ because the questionnaires are answered anonymously and individually by each member of the group.
- The answers are summarized and sent back to the group members along with the next questionnaire.
- This process is repeated until a group consensus is reached. This usually only takes two iterations, but can sometimes takes as many as six rounds before a consensus is reached

---
Suitability of Delphi method
Suitability of Delphi method
- The Delphi method is especially useful for futuristic Projects (long-range forecasting 20-30 years), as expert opinions are the only source of information available. Ex.Master plan
- Top secret and complex military projects
- When time & cost constraints make frequent face-to-face meetings difficult to arrange.
- When the heterogeneity of the participants must be preserved and anonymity assured.
- In situations where there is no clear-cut resolution of a given policy issue

---
Delphi positive
Delphi positive
- Anonymity can be guaranteed, anonymity for participants make contributions of ideas a safe activity
- Conducted in writing and does not require face-to-face meetings
- responses can be made at the convenience of the participant
- Opportunities for large number of experts to participate
- Opportunities for participants to reconsider their opinions
- Gives access to groups of widely dispersed experts
- Time for reflection, improving the strength of opinion.
- Participants have an equal say
- Greater acceptance of Delphi results than other consensus methods.
- Learning and motivating experience for participants.
- Highly cost-effective, when conducted by experts
- Relatively free of social pressure, personality influence, and individual dominance and is, therefore, conducive to independent thinking and gradual formulation of reliable judgments or forecasting of results

---
Delphi negative
Delphi negative
- Large amount of time to conduct several rounds
- The complexity of data analysis
- The difficulty of maintaining participant enthusiasm throughout process
- Potential of Low Response Rates Due to the multiple feedback processes
- The power of persuasion or prestigious individuals to shape group opinion
- The vulnerability of group dynamics to manipulation
- Manipulation, the responses can be altered by the monitors in the hope of moving the next round responses in a desired direction. Care needed in this regard
- The bandwagon effect of a majority opinion
- Ambiguity regarding panel size and consensus levels required

---
Story points (SP)_clipboard1
Story points (SP)
- Simplest Story = 2 SP
- Bigger Story = 5 SP
- Bigger One = 8 SP
- Weights come from Fibonacci Series: 1, 1, 2, 3, 5, 8, 13, 21

---
Planning poker
Planning poker
- Planning Poker is a consensus-based estimating technique.
- First defined by James Grenning in 2002.
- Mostly used in Scrum and Extreme Programming.
- Make the meetings more short and productive and create estimates with the involve of whole team.
- Avoid the influence of the other participants.
- Used deck of cards showing the Fibonacci sequence including a zero.

---
Type of cards im planning poker
Type of cards in planning poker
- 0, 1, 2, 3, 5, 8, 13, 20, 40, 100.
- 1, 2, 3, 5, 8, 13, BIG.
- ½, 1, 2, 3, 4, 5, 6, 7, ∞
- Some deck contain “don’t know”, “discuss”, “coffee time”
- Large numbers: Not everyone sticks to days as their unit of estimation

---
Procedure of planning poker
Procedure of planning poker
- At the estimation meeting, each estimator is given one set of the cards.
- A Moderator
  - Who will not play, chairs the meeting.
- The Product Manager
  - Provides a short overview. The team is given an opportunity clarify assumptions and risks. A summary of the discussion is recorded by the moderator.
- Each programmer selects their estimate cards.
- Everyone calls their cards simultaneously by turning them over.
- People with high estimates and low estimates are given a chance to justify their estimation.
- Repeat the estimation process until a consensus is reached. The developer who was likely to own the deliverable has a large portion vote, although the Moderator can negotiate the consensus.

---
Advantages of planning poker
Advantages of planning poker
- Discussions leads to accurate estimations.
- Everyone gives their opinions.
- Estimators get opportunity to justify their estimations.
- The ones estimating are the ones who will do the work.

---
Disadvantages of planning poker
Disadvantages of planning poker
- Estimation changes with the different skills and experience.
- Meetings may take longer time if its not managed well.
- Meetings with all the team members are expensive.

---
3-points estimating
3-points estimating
- Triangular distribution:
  E = (o + m + p ) / 3
  Where
  E is Estimate;
  o = optimistic estimate;
  p = pessimistic estimate;
  m = most likely (realistic) estimate
- Beta (or PERT):
  E = (o + 4m + p ) / 6

---
Key points
Key points
- There is not a simple relationship between the price charged for a system and its development costs.
- Factors affecting productivity include individual aptitude, domain experience, the development project, the project size, tool support and the working environment.
- Software may be priced to gain a contract and the functionality adjusted to the price.
- Different techniques of cost estimation should be used when estimating costs.
- The COCOMO model takes project, product, personnel and hardware attributes into account when predicting effort required.
- Algorithmic cost models support quantitative option analysis as they allow the costs of different options to be compared.
- The time to complete a project is not proportional to the number of people working on the project.