Project planning

---
Topics covered
Topics covered
- Plan-driven development
- Project scheduling
- Agile planning

---
Software Project Planning
Software Project Planning
- Estimating
  - Features and Priorities
  - Risk Assessment
  - Resources
- Scheduling
  - Tasks
  - Milestones
  - Deliverables

---
Project planning
Project planning
- Project planning involves breaking down the work into parts and assign these to project team members, anticipate problems that might arise and prepare tentative solutions to those problems.
- The project plan, which is created at the start of a project, is used to communicate how the work will be done to the project team and customers, and to help assess progress on the project.

---
Planning stages
Planning stages
- At the proposal stage, when you are bidding for a contract to develop or provide a software system.
- During the project startup phase, when you have to plan who will work on the project, how the project will be broken down into increments, how resources will be allocated across your company, etc.
- Periodically throughout the project, when you modify your plan in the light of experience gained and information from monitoring the progress of the work.

---
Proposal planning
Proposal planning
- Planning may be necessary with only outline software requirements.
- The aim of planning at this stage is to provide information that will be used in setting a price for the system to customers.
- Project pricing involves estimating how much the software will cost to develop, taking factors such as staff costs, hardware costs, software costs, etc. into account

---
Project startup planning
Project startup planning
- At this stage, you know more about the system requirements but do not have design or implementation information
- Create a plan with enough detail to make decisions about the project budget and staffing.
  - This plan is the basis for project resource allocation
- The startup plan should also define project monitoring mechanisms
- A startup plan is still needed for agile development to allow resources to be allocated to the project

---
Development planning
Development planning
- The project plan should be regularly amended as the project progresses and you know more about the software and its development
- The project schedule, cost-estimate and risks have to be regularly revised

---
Plan-driven development
Plan-driven development

---
Plan-driven development
Plan-driven development
- Plan-driven or plan-based development is an approach to software engineering where the development process is planned in detail.
  - Plan-driven development is based on engineering project management techniques and is the ‘traditional’ way of managing large software development projects.
- A project plan is created that records the work to be done, who will do it, the development schedule and the work products.
- Managers use the plan to support project decision making and as a way of measuring progress.

---
Plan-driven development – pros and cons
Plan-driven development
pros and cons
- The arguments in favor of a plan-driven approach are that early planning allows organizational issues (availability of staff, other projects, etc.) to be closely taken into account, and that potential problems and dependencies are discovered before the project starts, rather than once the project is underway.
- The principal argument against plan-driven development is that many early decisions have to be revised because of changes to the environment in which the software is to be developed and used.

---
Project plans
Project plans
- In a plan-driven development project, a project plan sets out the resources available to the project, the work breakdown and a schedule for carrying out the work.
- Plan sections
  - Introduction
  - Project organization
  - Risk analysis
  - Hardware and software resource requirements
  - Work breakdown
  - Project schedule
  - Monitoring and reporting mechanisms

---
Project plan supplements
Project plan supplements
Plan	Description
Configuration management plan	Describes the configuration management procedures and structures to be used.
Deployment plan	Describes how the software and associated hardware (if required) will be deployed in the customer’s environment. This should include a plan for migrating data from existing systems.
Maintenance plan	Predicts the maintenance requirements, costs, and effort.
Quality plan	Describes the quality procedures and standards that will be used in a project.
Validation plan	Describes the approach, resources, and schedule used for system validation.

---
The planning process
The planning process
- Project planning is an iterative process that starts when you create an initial project plan during the project startup phase.
- Plan changes are inevitable:
  - As more information about the system and the project team becomes available during the project, you should regularly revise the plan to reflect requirements, schedule and risk changes.
  - Changing business goals also leads to changes in project plans. As business goals change, this could affect all projects, which may then have to be re-planned.

---
The project planning process
The project planning process

---
Planning assumptions
Planning assumptions
- You should make realistic rather than optimistic assumptions when you are defining a project plan.
- Problems of some description always arise during a project, and these lead to project delays.
- Your initial assumptions and scheduling should therefore take unexpected problems into account.
- You should include contingency in your plan so that if things go wrong, then your delivery schedule is not seriously disrupted.

---
Project scheduling
Project scheduling

---
Project scheduling
Project scheduling
- Project scheduling is the process of deciding how the work in a project will be organized as separate tasks, and when and how these tasks will be executed.
- You estimate the calendar time needed to complete each task, the effort required and who will work on the tasks that have been identified.
- You also have to estimate the resources needed to complete each task, such as the disk space required on a server, the time required on specialized hardware, such as a simulator, and what the travel budget will be.

---
Project scheduling activities
Project scheduling activities
- Split project into tasks and estimate time and resources required to complete each task.
- Organize tasks concurrently to make optimal use of workforce.
- Minimize task dependencies to avoid delays caused by one task waiting for another to complete.
- Dependent on project managers intuition and experience.

---
The project scheduling process
The project scheduling process

---
Project duration and staffing
- As well as effort estimation, managers must estimate the calendar time required to complete a project and when staff will be required.
- Nominal schedule time can be estimated using a COCOMO2
- The time required is independent of the number of people working on the project.

---
Staffing requirements
- Staff required can’t be computed by diving the development time by the required schedule.
- The number of people working on a project varies depending on the phase of the project.
- The more people who work on the project, the more total effort is usually required.
- A very rapid build-up of people often correlates with schedule slippage.

---
Scheduling problems
Scheduling problems
- Estimating the difficulty of problems and hence the cost of developing a solution is hard.
- Productivity is not proportional to the number of people working on a task.
- Adding people to a late project makes it later because of management overheads.
- The unexpected always happens. Always allow contingency in planning.

---
Schedule presentation
Schedule presentation
- Graphical notations are normally used to illustrate the project schedule.
- These show the project breakdown into tasks. Tasks should not be too small. They should take about a week or two.
- Calendar-based
  - Bar charts are the most commonly used representation for project schedules. They show the schedule as activities or resources against time.
- Activity networks
  - Show task dependencies

---
Project activities
Project activities
- Project activities (tasks) are the basic planning element. Each activity has:
  - a duration in calendar days or months,
  - an effort estimate, which shows the number of person-days or person-months to complete the work,
  - a deadline by which the activity should be complete,
  - a defined end-point, which might be a document, the holding of a review meeting, the successful execution of all tests, etc.

---
Milestones and deliverables
Milestones and deliverables
- Milestones are points in the schedule against which you can assess progress, for example, the handover of the system for testing.
- Deliverables are work products that are delivered to the customer, e.g. a requirements document for the system.

---
Tasks, durations, and dependencies
Task	Effort (person-days)	Duration (days)	Dependencies
T1	15	10
T2	8	15
T3	20	15	T1 (M1)
T4	5	10
T5	5	10	T2, T4 (M3)
T6	10	5	T1, T2 (M4)
T7	25	20	T1 (M1)
T8	75	25	T4 (M2)
T9	10	15	T3, T6 (M5)
T10	20	15	T7, T8 (M6)
T11	10	10	T9 (M7)
T12	20	10	T10, T11 (M8)

---
Task dependency graph

---
Activity bar chart
Activity bar chart

---
Staff allocation chart
Staff allocation chart

---
Agile planning
Agile planning

---
Agile planning
Agile planning
- Agile methods of software development are iterative approaches where the software is developed and delivered to customers in increments.
- Unlike plan-driven approaches, the functionality of these increments is not planned in advance but is decided during the development.
  - The decision on what to include in an increment depends on progress and on the customer’s priorities.
- The customer’s priorities and requirements change so it makes sense to have a flexible plan that can accommodate these changes.

---
Planning in XP

---
Agile planning stages
Agile planning stages
- Release planning, which looks ahead for several months and decides on the features that should be included in a release of a system.
- Iteration planning, which has a shorter term outlook, and focuses on planning the next increment of a system. This is typically 2-4 weeks of work for the team.

---
Approaches to agile planning
Approaches to agile planning
- Planning in Scrum
- Based on managing a project backlog (things to be done) with daily reviews of progress and problems
- The planning game
  - Developed originally as part of Extreme Programming (XP)
  - Dependent on user stories as a measure of progress in the project

---
Story-based planning
Story-based planning
- The planning game is based on user stories that reflect the features that should be included in the system.
- The project team read and discuss the stories and rank them in order of the amount of time they think it will take to implement the story.
- Stories are assigned ‘effort points’ reflecting their size and difficulty of implementation
- The number of effort points implemented per day is measured giving an estimate of the team’s ‘velocity’
- This allows the total effort required to implement the system to be estimated

---
The planning game
The planning game

---
Release and iteration planning
Release and iteration planning
- Release planning involves selecting and refining the stories that will reflect the features to be implemented in a release of a system and the order in which the stories should be implemented.
- Stories to be implemented in each iteration are chosen, with the number of stories reflecting the time to deliver an iteration (usually 2 or 3 weeks).
- The team’s velocity is used to guide the choice of stories so that they can be delivered within an iteration.

---
Task allocation
Task allocation
- During the task planning stage, the developers break down stories into development tasks.
  - A development task should take 4–16 hours.
  - All of the tasks that must be completed to implement all of the stories in that iteration are listed.
  - The individual developers then sign up for the specific tasks that they will implement.
- Benefits of this approach:
  - The whole team gets an overview of the tasks to be completed in an iteration.
  - Developers have a sense of ownership in these tasks and this is likely to motivate them to complete the task.

---
Software delivery
Software delivery
- A software increment is always delivered at the end of each project iteration.
- If the features to be included in the increment cannot be completed in the time allowed, the scope of the work is reduced.
- The delivery schedule is never extended.

---
Agile planning difficulties
Agile planning difficulties
- Agile planning is reliant on customer involvement and availability.
- This can be difficult to arrange, as customer representatives sometimes have to prioritize other work and are not available for the planning game.
- Furthermore, some customers may be more familiar with traditional project plans and may find it difficult to engage in an agile planning process.

---
Agile planning applicability
Agile planning applicability
- Agile planning works well with small, stable development teams that can get together and discuss the stories to be implemented.
- However, where teams are large and/or geographically distributed, or when team membership changes frequently, it is practically impossible for everyone to be involved in the collaborative planning that is essential for agile project management.

---
Key points
- Plan-driven development is organized around a complete project plan that defines the project activities, the planned effort, the activity schedule and who is responsible for each activity.
- Project scheduling involves the creation of graphical representations the project plan. Bar chartsshow the activity duration and staffing timelines, are the most commonly used schedule representations.
- A project milestone is a predictable outcome of an activity or set of activities. At each milestone, a formal report of progress should be presented to management. A deliverable is a work product that is delivered to the project customer.
- The agile planning game involves the whole team in project planning. The plan is developed incrementally and, if problems arise, it is adjusted so that software functionality is reduced instead of delaying the delivery of an increment.
- The XP planning game involves the whole team in project planning. The plan is developed incrementally and, if problems arise, is adjusted. Software functionality is reduced instead of delaying delivery of an increment.